## Sheet1
FILLING THINGS THAT ARE COMPLETED IN WITH GREEN
Component | Task | Requirement Specification | Application Feature | Time Estimate (Hours) | SWE Activity | Component List
Open Route Service | Reuse Byfer Code for getting JSON response from service. | Getting distance matrix between set of locations. |  | Completed | Software Reuse | Open Route Service
| Write JUnit tests for time distances from response. |  |  | 3 | Software Testing
| Perform quality assurance test using ORSfactory |  |  | 1 | Software Quality
User Interface | Develop architecture for the document screen from use cases. |  | Application User Interface | 1
| Write a document on how the user interface fulfills each usecase. |  |  | 1 | Software Specification
| Design user selection of database from supported set of databases. | Allow input of mongo database for location index of orders and drivers. |  | 2 |  | User Interface
| Design user input of database connection credentials. |  |  | 1 |  | Dataset Interface
| Check for database status. |  |  | Completed | Software Reliability | Algorithm
| Design user input for run curate dataset from database. |  |  | 4 |  | Documentation
| Design user input for run algorithm. |  |  | 4 |  | Parser
| Design user input for exporting results. |  |  | 4
| Design display of results to screen. | Display the average time to delivery. |  | 4
| Graphically display the difference in average wait time vs drivers. |  |  | 5
| Check for correct database size. | Must be a minimum 25 restaurants available to order from. |  | 2
| Create a testing document for user interface. |  |  | 3 | Software Testing
| Perform quality assurance test. |  |  | 1 | Software Quality
Dataset Interface | Research area of interest and define area of service for FreshFood. (DECIDED ON JERSEY CITY) |  | Database Management Integration
| Curate dataset of 25-50 restaurants. (WE HAVE 168 RESTAURANTS) | Must be a minimum 25 restaurants available to order from.
| Curate dataset of 1000 possible dropoff locations. (WE HAVE 4900 LOCATIONS) | Must be able to handle up to 1000 hours at a time.
| Create standardized database format. | Documentation for Fresh Food interaction with the system. | Support for different databases
| Write code for getting collection from user database. | Application interface for uploading to database the company wishes to use.
Define methods for interacting with supported databases and returning JSON.
| Implement methods for notifying user of incorrect data input or otherwise failure to interface with database or open file. |  |  |  | Dependable Engineering
Parser | Define methods for parsing JSON response from Dataset Interface and returning usable data. |  | Support for different databases
Research database JSON response for MongoDB and other supported database.
Write code for parsing JSON response for supported databases.
Algorithm | Generate workflow for algorithm behavior.
| Write code for creating query for ORS. |  |  | Completed.
Documentation | Generate database format document for supported databases.
Generate javadoc.
Please put anything else you can think of such as where we host our dataset, instructions on how to use it.
Class Diagram
| Develop a use case diagram for FreshTime. |  |  | Completed
Draft MongoDB Format Document
Implement ORS Backend API
Generate Gantt Diagram