## Sheet1
FILLING THINGS THAT ARE COMPLETED IN WITH GREEN
Component | Task | Requirement Specification | Application Feature | Time Estimate (Hours) | SWE Activity | Component List
Open Route Service | Reuse Byfer Code for getting JSON response from service. | Getting distance matrix between set of locations. |  | Completed | Software Reuse | Open Route Service
| Write JUnit tests for time distances from response. |  |  | 3 | Software Testing
| Perform quality assurance test using ORSfactory |  |  | 1 | Software Quality
User Interface | Develop architecture for the document screen from use cases. |  | Application User Interface | 1
| Write a document on how the user interface fulfills each usecase. |  |  | 1 | Software Specification
| Design user selection of database from supported set of databases. | Allow input of mongo database for location index of orders and drivers. |  | 2 |  | User Interface
| Design user input of database connection credentials. |  |  | 1 |  | Dataset Interface
| Check for database status. |  |  | Completed | Software Reliability | Algorithm
| Design user input for run curate dataset from database. |  |  | 4 |  | Documentation
| Design user input for run algorithm. |  |  | 4 |  | Parser
| Design user input for exporting results. |  |  | 4
| Design display of results to screen. | Display the average time to delivery. |  | 4
| Graphically display the difference in average wait time vs drivers. |  |  | 5
| Check for correct database size. [Software] | Must be a minimum 25 restaurants available to order from. |  | 2
| Create a testing document for user interface. |  |  | 3 | Software Testing
| Perform quality assurance test. |  |  | 1 | Software Quality
Dataset Interface | Research area of interest and define area of service for FreshFood. (DECIDED ON JERSEY CITY) |  | Database Management Integration
| Curate dataset of 25-50 restaurants. (WE HAVE 168 RESTAURANTS) | Must be a minimum 25 restaurants available to order from.
| Curate dataset of 1000 possible dropoff locations. (WE HAVE 4900 LOCATIONS) | Must be able to handle up to 1000 hours at a time.
| Create standardized database format. | Documentation for Fresh Food interaction with the system. | Support for different databases
| Write code for getting collection from user database. | Application interface for uploading to database the company wishes to use.
Define methods for interacting with supported databases and returning JSON.
| Implement methods for notifying user of incorrect data input or otherwise failure to interface with database or open file. |  |  |  | Dependable Engineering
Parser | Define methods for parsing JSON response from Dataset Interface and returning usable data. |  | Support for different databases
Research database JSON response for MongoDB and other supported database.
Write code for parsing JSON response for supported databases.
Algorithm | Generate workflow for algorithm behavior.
| Write code for creating query for ORS. |  |  | Completed.
Documentation | Generate database format document for supported databases.
Generate javadoc.
Class Diagram
| Develop a use case diagram for FreshTime. |  |  | Completed
Draft MongoDB Format Document
Generate Gantt Diagram
Generate State Diagram
Generate Sequence Diagram